## Rollout Plan
Application Security Program — 3-Month Rollout Plan ¦ Aug – Oct 2026
|  | August 2026 |  |  |  | September 2026 |  |  |  | October 2026
| Month | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Environment Setup & Access Provisioning | August | bar: August 2026 W1 to August 2026 W2
Dashboard & Reporting Setup | August
Developer Onboarding | August | bar: August 2026 W2 to August 2026 W3
Developer Training Sessions | August
Pilot Scan — Priority Repositories | August | bar: August 2026 W4
Initial Findings Review | September
Rule Configuration & Tuning | September | bar: September 2026 W1 to September 2026 W2
Full Repository Scan | September
Findings Triage & Prioritisation | October | bar: October 2026 W1 to October 2026 W2
Remediation Tracking | October
Risk Assessment & Reporting | October | bar: October 2026 W3 to October 2026 W4
Shaded cells indicate active task weeks. |  | August 2026 W2: Active